## Project Plan
Phase / Task | Start Date | End Date | Week 1 11.05. | Week 2 18.05. | Week 3 25.05. | Week 4 01.06. | Week 5 08.06. | Week 6 15.06.
Phase 1: Requirements Analysis | 11.05.2026 | 17.05.2026 | Phase 1
Define MoSCoW requirements (Must, Should, Could, Won't) | 11.05.2026 | 17.05.2026
Define non-functional requirements | 11.05.2026 | 17.05.2026
Write "Introduction & Context" documentation | 11.05.2026 | 17.05.2026
Create Spotify Dev Account & get API Keys | 11.05.2026 | 17.05.2026
Phase 2: Design Phase | 18.05.2026 | 24.05.2026 |  | Phase 2
Draw UML Activity Diagram | 18.05.2026 | 24.05.2026
Draw UML Component Diagram (API, SQLite, Filesystem) | 18.05.2026 | 24.05.2026
Design local environment (.env) architecture | 18.05.2026 | 24.05.2026
Phase 3: Development Phase | 25.05.2026 | 07.06.2026 |  |  | Phase 3
W3: Implement Spotify API OAuth & fetch data | 25.05.2026 | 31.05.2026
W3: Setup local SQLite DB & insert track data | 25.05.2026 | 31.05.2026
W4: Program aggregation logic (calc minutes, top artists) | 01.06.2026 | 07.06.2026
W4: Program report generator (PDF/TXT output) & cleanup code | 01.06.2026 | 07.06.2026
Phase 4: Testing Phase | 08.06.2026 | 14.06.2026 |  |  |  |  | Phase 4
Define test cases & edge cases | 08.06.2026 | 14.06.2026
Execute tests & document logs/screenshots | 08.06.2026 | 14.06.2026
Fix identified bugs | 08.06.2026 | 14.06.2026
Phase 5: Deployment & Documentation Phase | 15.06.2026 | 19.06.2026 | [5 empty] | Phase 5
Setup local OS Task Scheduler for weekly execution | 15.06.2026 | 19.06.2026
Write "Instructions & Setup" guide | 15.06.2026 | 19.06.2026
Final review against M122E grading rubric | 15.06.2026 | 19.06.2026
Legend
Phase 1 | Requirements Analysis |  | Hellblau
Phase 2 | Design Phase |  | Orange
Phase 3 | Development Phase |  | Grün
Phase 4 | Testing Phase |  | Gelb
Phase 5 | Deployment & Documentation |  | Violett